## Clarification Q&A
ESKOM eDNA to PI Upgrade – Clarification Questions and Answers
This document lists all formal questions and clarification requests related to the ESKOM eDNA to PI Upgrade RFP.
No. | RFP Section / Reference | Question / Clarification | Person raising the question | Impact Level | Client Response
1 |  | Please clarify if Eskom is expecting the vendor to setup an Asset Framework structure in the new PI installation. This is a really important clarification as this affects the migration strategy and timelines. Please note that if an AF needs to be created with new tags these need to mapped to the old tags in eDNA and this is a very time consuming exercise, especially when importing historical data. The other option is to import tags as they are in the eDNA system with minor changes to the tag name. This is more straight forward but it will render the use of AF pointless as we will not be utilising the AF features. Therefore to clarify please choose which option: Option 1: Asset framework structure with new tags utilising all the AF features Option 2: Migrate all eDNA tags to PI and do not use the AF structure and features (Pure tag and data migration) like to like in eDNA with minor changes to tag name so it can be replicated in PI |  |  | AF configuration is a requirement. Eskom has already provided a spreadsheet that defines the expected AF breakdown. Historic data needs to be mapped to the new AF tag position. This will be closes to Option 1.
2 |  | Depending on how the Eskom current eDNA archives are setup, migration may be a subject to compute power and storage rather than engineering resources i.e. people. In other words, vendors may not be in control of how long it will take to export data from eDNA and import to PI as this is a function of the processing power available from Eskom as well as the capabiltiy of the eDNA software to export the data. In this case is Eskom open to performing the migration in stages, where the core objective of the build phase will be to setup the new PI system, tags and interfaces, whiilst migration of data is moved or overlaps into the support phase? |  |  | Configuration and migration need to be part of the contract phase.
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40